## Bug List
DAFTAR BUG & TRACEABILITY KE TEST CASE
Origin 'Asli' = sudah ada di file awal. Origin 'Baru' = draft yang dibuat dari temuan Test Case yang belum punya bug report. Severity pada bug baru masih usulan dan perlu dikonfirmasi tester.
Bug ID | Module / Menu | Severity | Test Case Ref (baris) | Origin | Short title
BUG_001 | Task - Add Task | Medium | Skenario B step 2 (baris 30) | Asli | Mandatory Class field: no red state / no required message
BUG_002 | Task - Add Task | Minor | Skenario B step 3,4,5 (baris 35,40,46) | Asli | No invalid-input feedback on dropdown fields
BUG_003 | Task - Add Task | Minor | Skenario B step 7 (baris 54) | Asli | Selected Due date cannot be cleared
BUG_004 | Task - Notification | Major | Skenario E step 3 (baris 125-130) | Asli (diperbaiki total) | TASK_N5 notification not received
BUG_005 | Task - Menu / Add Task | Minor | Skenario A step 2 (13), B step 1 (26) | Baru | French labels Taches / Ajoute une tache
BUG_006 | Navigation menu | Minor | Skenario A step 3 (baris 15) | Baru | Messages & Export menu not highlighted
BUG_007 | Task - Add Task | Minor | Skenario B step 2 (baris 29) | Baru | Priority mandatory without asterisk
BUG_008 | Task - Add Task | Medium | Skenario B step 6 (baris 47) | Baru | Priority pre-selected to 1 by default
BUG_009 | Task - Add Task | Minor | Skenario B step 7 (baris 53) | Baru | Due date format DD/MM/YYYY on Add Task pop up
BUG_010 | Task - Detail pop up | Minor | Skenario D step 3 (102), F step 4 (144) | Baru | Due date format MMM DD, YYYY on detail pop up
BUG_011 | Task - Add Task | Medium | Skenario B step 9 (baris 57-58) | Baru | Submit button not always active, no mandatory alert
BUG_012 | Task - Add Task | Medium | Skenario B step 7 (baris 51) | Baru | Past date selectable as Due date
BUG_013 | Task - Add Task | Medium | Skenario B step 5 (baris 42) | Baru | User search by First name not working
BUG_014 | Task - Detail pop up | Major | Skenario F step 7-8 (baris 155-158) | Baru | Detail pop up does not open for Done task
BUG_015 | User / Mailbox menu | Medium | Skenario C step 1,3 (baris 70,71,76,77) | Baru (perlu konfirmasi scope) | User menu & 'Connect as' not available

## Example
Bug ID | BUG_001
Reporter | Jeremia Imanuel Werung
Severity | Medium
Summary | Mandatory Class field does not turn RED and shows no 'required' message when it is left empty
Description | On the Add Task pop up the Class field is mandatory, but when it is left empty it does not turn RED and no 'the field is required' message is displayed, unlike the other mandatory fields.
Reproducability Rate | Permanent
Attachment | https://drive.google.com/file/d/1iCIeM_D7b0a7c2opbGzg9n2XqD_A4_s6/view?usp=drive_link
Step to Reproduce | 1. Access this url https://candidate-test.zetta-demo.space/ 2. Go to field user email 3. Put the user email: jeremia.werung@yopmail.com 4. Go to field password 5. Put password: Jeremia1234@ 6. Click on login button 7. Click on Task menu 8. Click on Add Task button 9. Fill in all mandatory fields except the Class field 10. Leave the Class field empty, then click outside the field and try to submit the form 11. Observe the Class field border and the message under the field
Expectation | Verify the field will become RED if it is mandatory and it is not filled and display text that the field is required
Actual Result | The Class field does not become RED and does not display a text that the field is required, although it is mandatory.
Environment | Browser: Google Chrome version 145.0.7632.76 (Official Build) (64-bit) CPU: 11th Gen Intel(R) Core(TM) i5-11320H @ 3.20GHz (3.19 GHz) RAM: 16 GB
Bug ID | BUG_002
Reporter | Jeremia Imanuel Werung
Severity | Minor
Summary | No invalid-input feedback when free text is typed into RNCP Title / Class / User field without selecting an item from the dropdown
Description | On the Add Task pop up, typing free text into the 'Select Title', 'Select Class' or 'User' field without picking an item from the dropdown list is silently ignored: the platform gives no message that the input is invalid. Affects Test Case scenario B step 3, 4 and 5.
Reproducability Rate | 3 times occur from 3 attempts
Attachment | -
Step to Reproduce | 1. Access this url https://candidate-test.zetta-demo.space/ 2. Go to field user email 3. Put the user email: jeremia.werung@yopmail.com 4. Go to field password 5. Put password: Jeremia1234@ 6. Click on login button 7. Click on Task menu 8. Click on Add Task button 9. Type free text into the 'Select Title' field without selecting any item from the dropdown list 10. Click outside the field and observe the field state and any message 11. Repeat step 9-10 for the 'Select Class' field and for the 'User' field
Expectation | If I just type on the field without selecting it from dropdown list, it will consider my input is invalid and there must be an information to me that the input is invalid
Actual Result | The input is neither accepted nor rejected: no information is displayed to tell that the typed input is invalid.
Environment | Browser: Google Chrome version 145.0.7632.76 (Official Build) (64-bit) CPU: 11th Gen Intel(R) Core(TM) i5-11320H @ 3.20GHz (3.19 GHz) RAM: 16 GB
Bug ID | BUG_003
Reporter | Jeremia Imanuel Werung
Severity | Minor
Summary | The selected Due date cannot be cleared from the 'Due date' field
Description | Once a date has been selected on the Add Task pop up, the value can no longer be deleted or cleared from the Due date field.
Reproducability Rate | Permanent
Attachment | -
Step to Reproduce | 1. Access this url https://candidate-test.zetta-demo.space/ 2. Go to field user email 3. Put the user email: jeremia.werung@yopmail.com 4. Go to field password 5. Put password: Jeremia1234@ 6. Click on login button 7. Click on Task menu 8. Click on Add Task button 9. Click on the 'Due date' field and select any date from the date selector 10. Try to clear the field by deleting the selected date (backspace / delete / clear icon)
Expectation | I must be able to clear the data on the 'due date' field by deleting the current date I selected
Actual Result | Cannot clear the data on the 'due date' field by deleting the current date that was selected.
Environment | Browser: Google Chrome version 145.0.7632.76 (Official Build) (64-bit) CPU: 11th Gen Intel(R) Core(TM) i5-11320H @ 3.20GHz (3.19 GHz) RAM: 16 GB
Bug ID | BUG_004
Reporter | Jeremia Imanuel Werung
Severity | Major
Summary | Notification TASK_N5 (task completed) is not received in the task creator's mailbox
Description | After the assigned user completes the task, the task creator does not receive the TASK_N5 notification in his mailbox. As a consequence the notification text (EN/FR), the signatory, the completion date and the link to the task cannot be verified at all. Affects Test Case scenario E step 3.
Reproducability Rate | 7 times occur from 7 attempts
Attachment | https://drive.google.com/file/d/1zNSPwl5hxx9iTNJErF5-HRmAhPM-8kpo/view?usp=drive_link
Step to Reproduce | 1. Login as the Operator who creates the task (jeremia.werung@yopmail.com / Jeremia1234@) 2. Click on Task menu, click Add Task and create a task assigned to another user 3. Login as the user who is assigned to the task 4. Open the task from the Task table, set the toggle to 'Achieved' and submit it 5. Login back as the Operator who created the task 6. Go to Mailbox menu and stay on the default 'To' tab 7. Look for the TASK_N5 notification of the completed task
Expectation | The creator receives the TASK_N5 notification in his mailbox; the notification text respects the notification document in English and French, the signatory is the user who completed the task, the completion date is accurate, the link opens the task pop up in the current tab, and opening the link without being logged in redirects to the login page.
Actual Result | No TASK_N5 notification is received in the creator's mailbox, so none of the expected points above can be verified.
Environment | Browser: Google Chrome version 145.0.7632.76 (Official Build) (64-bit) CPU: 11th Gen Intel(R) Core(TM) i5-11320H @ 3.20GHz (3.19 GHz) RAM: 16 GB
Bug ID | BUG_005
Reporter | Jeremia Imanuel Werung
Severity | Minor
Summary | French labels of the Task menu and of the Add Task button do not match the requirement
Description | In French, the Task menu is displayed as 'Taches' while the requirement expects 'Tache', and the Add Task button is displayed as 'Ajoute une tache' while the requirement expects 'Ajoute une taches'. Affects Test Case scenario A step 2 and scenario B step 1.
Reproducability Rate | Permanent (to be confirmed by tester)
Attachment | -
Step to Reproduce | 1. Access this url https://candidate-test.zetta-demo.space/ 2. Go to field user email 3. Put the user email: jeremia.werung@yopmail.com 4. Go to field password 5. Put password: Jeremia1234@ 6. Click on login button 7. Switch the platform language to French 8. Observe the Task menu label on the menu list 9. Click on the Task menu, then observe the label of the Add Task button
Expectation | [English] Tasks / [France] Tache for the menu, and [English] Add Task / [France] Ajoute une taches for the button, as stated in the requirement.
Actual Result | Menu is displayed as 'Taches' and the button as 'Ajoute une tache'.
Environment | Browser: Google Chrome version 145.0.7632.76 (Official Build) (64-bit) CPU: 11th Gen Intel(R) Core(TM) i5-11320H @ 3.20GHz (3.19 GHz) RAM: 16 GB
Bug ID | BUG_006
Reporter | Jeremia Imanuel Werung
Severity | Minor
Summary | Messages and Export menus are not highlighted in yellow when they are selected
Description | The active-menu highlight is not applied to the Messages and Export menus, while it works on the other menus. Affects Test Case scenario A step 3.
Reproducability Rate | Permanent (to be confirmed by tester)
Attachment | -
Step to Reproduce | 1. Access this url https://candidate-test.zetta-demo.space/ 2. Go to field user email 3. Put the user email: jeremia.werung@yopmail.com 4. Go to field password 5. Put password: Jeremia1234@ 6. Click on login button 7. Click on the Messages menu 8. Observe whether the selected menu is highlighted in yellow 9. Click on the Export menu and observe the same behaviour
Expectation | The selected menu is highlighted in yellow once it is selected.
Actual Result | Messages and Export menus stay un-highlighted when they are selected.
Environment | Browser: Google Chrome version 145.0.7632.76 (Official Build) (64-bit) CPU: 11th Gen Intel(R) Core(TM) i5-11320H @ 3.20GHz (3.19 GHz) RAM: 16 GB
Bug ID | BUG_007
Reporter | Jeremia Imanuel Werung
Severity | Minor
Summary | Priority field is mandatory but its label has no asterisk (*)
Description | On the Add Task pop up, the Priority field is mandatory but the asterisk marker is missing on its label, while RNCP Title, Class, User, Due Date and Description all have it. Affects Test Case scenario B step 2.
Reproducability Rate | Permanent (to be confirmed by tester)
Attachment | -
Step to Reproduce | 1. Access this url https://candidate-test.zetta-demo.space/ 2. Go to field user email 3. Put the user email: jeremia.werung@yopmail.com 4. Go to field password 5. Put password: Jeremia1234@ 6. Click on login button 7. Click on Task menu 8. Click on Add Task button 9. Observe the labels of all mandatory fields on the pop up
Expectation | All mandatory fields (RNCP Title, Class, User, Priority, Due Date, Description) show an asterisk (*) on the label.
Actual Result | The Priority label has no asterisk although the field is mandatory.
Environment | Browser: Google Chrome version 145.0.7632.76 (Official Build) (64-bit) CPU: 11th Gen Intel(R) Core(TM) i5-11320H @ 3.20GHz (3.19 GHz) RAM: 16 GB
Bug ID | BUG_008
Reporter | Jeremia Imanuel Werung
Severity | Medium
Summary | Priority is pre-selected to option 1 by default on the Add Task pop up
Description | When the Add Task pop up is opened, Priority already has option 1 selected instead of being empty, so a task can be created with a priority the user never chose. Affects Test Case scenario B step 6.
Reproducability Rate | Permanent (to be confirmed by tester)
Attachment | -
Step to Reproduce | 1. Access this url https://candidate-test.zetta-demo.space/ 2. Go to field user email 3. Put the user email: jeremia.werung@yopmail.com 4. Go to field password 5. Put password: Jeremia1234@ 6. Click on login button 7. Click on Task menu 8. Click on Add Task button 9. Observe the Priority field before touching it
Expectation | By default no priority option is selected.
Actual Result | Priority is already selected on option 1 when the pop up is opened.
Environment | Browser: Google Chrome version 145.0.7632.76 (Official Build) (64-bit) CPU: 11th Gen Intel(R) Core(TM) i5-11320H @ 3.20GHz (3.19 GHz) RAM: 16 GB
Bug ID | BUG_009
Reporter | Jeremia Imanuel Werung
Severity | Minor
Summary | Due date on the Add Task pop up is displayed as DD/MM/YYYY instead of DD Month YYYY
Description | After picking a date, the Due date field shows a numeric format (example: 19/02/2026) instead of the format required by the document (example: 12 June 2021). Affects Test Case scenario B step 7.
Reproducability Rate | Permanent (to be confirmed by tester)
Attachment | -
Step to Reproduce | 1. Access this url https://candidate-test.zetta-demo.space/ 2. Go to field user email 3. Put the user email: jeremia.werung@yopmail.com 4. Go to field password 5. Put password: Jeremia1234@ 6. Click on login button 7. Click on Task menu 8. Click on Add Task button 9. Click on the 'Due date' field and select any date 10. Observe the format displayed in the field
Expectation | The date format displayed on the pop up is DD Month YYYY (example: 12 June 2021).
Actual Result | The date is displayed as 19/02/2026 (DD/MM/YYYY).
Environment | Browser: Google Chrome version 145.0.7632.76 (Official Build) (64-bit) CPU: 11th Gen Intel(R) Core(TM) i5-11320H @ 3.20GHz (3.19 GHz) RAM: 16 GB
Bug ID | BUG_010
Reporter | Jeremia Imanuel Werung
Severity | Minor
Summary | Due date on the task detail pop up is displayed as MMM DD, YYYY instead of DD Month YYYY
Description | On the task detail pop up the due date is shown as 'Nov 17, 2025'. The same wrong format appears for the assigned user and for the task creator. Affects Test Case scenario D step 3 and scenario F step 4.
Reproducability Rate | Permanent (to be confirmed by tester)
Attachment | -
Step to Reproduce | 1. Access this url https://candidate-test.zetta-demo.space/ 2. Go to field user email 3. Put the user email: jeremia.werung@yopmail.com 4. Go to field password 5. Put password: Jeremia1234@ 6. Click on login button 7. Click on Task menu 8. Click on a task in the List of Task table to open the task detail pop up 9. Observe the due date format displayed on the pop up
Expectation | The due date is displayed as DD Month YYYY (example: 28 June 2021).
Actual Result | The due date is displayed as 'Nov 17, 2025' (MMM DD, YYYY).
Environment | Browser: Google Chrome version 145.0.7632.76 (Official Build) (64-bit) CPU: 11th Gen Intel(R) Core(TM) i5-11320H @ 3.20GHz (3.19 GHz) RAM: 16 GB
Bug ID | BUG_011
Reporter | Jeremia Imanuel Werung
Severity | Medium
Summary | Submit button on Add Task pop up is not always active and no mandatory-field alert is displayed
Description | The requirement asks for a permanently active Submit button that raises an alert when mandatory fields are still empty. In the build the button is disabled until every mandatory field is filled, so the alert can never be triggered. Affects Test Case scenario B step 9.
Reproducability Rate | Permanent (to be confirmed by tester)
Attachment | -
Step to Reproduce | 1. Access this url https://candidate-test.zetta-demo.space/ 2. Go to field user email 3. Put the user email: jeremia.werung@yopmail.com 4. Go to field password 5. Put password: Jeremia1234@ 6. Click on login button 7. Click on Task menu 8. Click on Add Task button 9. Leave one or more mandatory fields empty 10. Observe the state of the Submit button and try to click it
Expectation | Submit button is always active; clicking it while mandatory fields are empty displays an alert asking the user to fill all mandatory fields.
Actual Result | Submit button stays disabled while mandatory fields are empty, it cannot be clicked and no alert is displayed.
Environment | Browser: Google Chrome version 145.0.7632.76 (Official Build) (64-bit) CPU: 11th Gen Intel(R) Core(TM) i5-11320H @ 3.20GHz (3.19 GHz) RAM: 16 GB
Bug ID | BUG_012
Reporter | Jeremia Imanuel Werung
Severity | Medium
Summary | Date selector of the Due date field allows past dates to be selected
Description | The Due date picker on the Add Task pop up allows past dates, so a task can be created with a deadline that is already over. Affects Test Case scenario B step 7.
Reproducability Rate | Permanent (to be confirmed by tester)
Attachment | -
Step to Reproduce | 1. Access this url https://candidate-test.zetta-demo.space/ 2. Go to field user email 3. Put the user email: jeremia.werung@yopmail.com 4. Go to field password 5. Put password: Jeremia1234@ 6. Click on login button 7. Click on Task menu 8. Click on Add Task button 9. Click on the 'Due date' field to open the date selector 10. Try to select a date before today
Expectation | Only present and future dates can be selected.
Actual Result | Past dates can also be selected and are accepted as the Due date.
Environment | Browser: Google Chrome version 145.0.7632.76 (Official Build) (64-bit) CPU: 11th Gen Intel(R) Core(TM) i5-11320H @ 3.20GHz (3.19 GHz) RAM: 16 GB
Bug ID | BUG_013
Reporter | Jeremia Imanuel Werung
Severity | Medium
Summary | User cannot be searched by First name in the User field of the Add Task pop up
Description | Searching the recipient in the User field only returns a result when the Last name is typed; typing the First name returns nothing. Test data: Lucas Jhonson. Affects Test Case scenario B step 5.
Reproducability Rate | Permanent (to be confirmed by tester)
Attachment | -
Step to Reproduce | 1. Access this url https://candidate-test.zetta-demo.space/ 2. Go to field user email 3. Put the user email: jeremia.werung@yopmail.com 4. Go to field password 5. Put password: Jeremia1234@ 6. Click on login button 7. Click on Task menu 8. Click on Add Task button 9. Click on the User field 10. Type the First name of an existing user (example: Lucas) and observe the result 11. Type the Last name of the same user (example: Jhonson) and observe the result
Expectation | A user can be found by typing either his/her First name or Last name in the User field.
Actual Result | Only the Last name returns a result; searching by First name returns no user.
Environment | Browser: Google Chrome version 145.0.7632.76 (Official Build) (64-bit) CPU: 11th Gen Intel(R) Core(TM) i5-11320H @ 3.20GHz (3.19 GHz) RAM: 16 GB
Bug ID | BUG_014
Reporter | Jeremia Imanuel Werung
Severity | Major
Summary | Task detail pop up does not open for a task that is already in 'Done' status
Description | As the task creator, clicking a task whose status is already Done does not open the detail pop up, so the Action taken filled by the assignee and the current Pending/Achieved status cannot be reviewed at all. Affects Test Case scenario F step 7 and step 8.
Reproducability Rate | Permanent (to be confirmed by tester)
Attachment | -
Step to Reproduce | 1. Login as the Operator who created a task (jeremia.werung@yopmail.com / Jeremia1234@) 2. Make sure the assigned user has completed the task with the 'Achieved' toggle, so its status is Done 3. Click on Task menu 4. Click on the task whose status is Done in the List of Task table
Expectation | The task detail pop up opens and shows the Action taken filled by the assigned user and the current status of the task; the Pending/Achieved toggle is hidden once the task is Achieved.
Actual Result | The detail pop up does not open for a Done task, so Action taken and current status cannot be seen.
Environment | Browser: Google Chrome version 145.0.7632.76 (Official Build) (64-bit) CPU: 11th Gen Intel(R) Core(TM) i5-11320H @ 3.20GHz (3.19 GHz) RAM: 16 GB
Bug ID | BUG_015
Reporter | Jeremia Imanuel Werung
Severity | Medium
Summary | User menu and the 'Connect as' feature are not available under the Mailbox menu
Description | The User menu described in the requirement is not present under Mailbox (only a Tutorials menu is shown), so the List of user table and the 'Connect as' (incognito) button cannot be reached. To be confirmed with the product owner whether this menu is out of scope for this build; if it is, the related test cases should stay N/A instead of being treated as a defect. Affects Test Case scenario C step 1 and step 3.
Reproducability Rate | Permanent (to be confirmed by tester)
Attachment | -
Step to Reproduce | 1. Access this url https://candidate-test.zetta-demo.space/ 2. Go to field user email 3. Put the user email: jeremia.werung@yopmail.com 4. Go to field password 5. Put password: Jeremia1234@ 6. Click on login button 7. Observe the menu list under the Mailbox menu 8. Look for a User menu and open it 9. On the List of user table, look for the 'Connect as' button in the Action column
Expectation | A User menu is available under Mailbox, it opens the List of user table, and the Action column provides a 'Connect as' (incognito) button.
Actual Result | Only a Tutorials menu is displayed under Mailbox: no User menu and no 'Connect as' button.
Environment | Browser: Google Chrome version 145.0.7632.76 (Official Build) (64-bit) CPU: 11th Gen Intel(R) Core(TM) i5-11320H @ 3.20GHz (3.19 GHz) RAM: 16 GB

## Revision Notes
CATATAN REVISI - Bug Report (dokumen asli oleh Jeremia Imanuel Werung)
Bagian | Kondisi di file asli | Koreksi yang dilakukan
BUG_004 - Step to Reproduce / Expectation / Actual Result | Ketiga field tertukar dan tidak logis: 'Step to Reproduce' berisi kalimat expected result, 'Expectation' berisi kalimat hasil aktual yang negatif ('I cannot see...'), dan 'Actual Result' berisi 'Can check the notification received from user' yang justru berlawanan dengan isi Description. | Ditulis ulang: Step to Reproduce berisi langkah reproduksi nyata, Expectation berisi perilaku yang diharapkan, Actual Result berisi hasil sebenarnya (notifikasi TASK_N5 tidak diterima).
BUG_004 - Severity | Medium. | Diusulkan Major karena notifikasi wajib tidak terkirim sama sekali dan memblokir 5 verifikasi lain. ASUMSI: skala severity tim belum diketahui, mohon dikonfirmasi.
BUG_001 - Summary & Description | 'Class filled Mandatory but dont have Red Dispaly if the filled dont have data input' - typo (Dispaly, dont) dan sulit dibaca; Description hanya menyalin Actual Result. | Summary ditulis ulang singkat dan jelas; Description menjelaskan konteks (di pop up Add Task, berbeda dari field mandatory lain).
BUG_001/002/003 - Step to Reproduce | Langkah berhenti sebelum aksi yang memicu bug (mis. 'Input all the data field beiside Class field' tanpa langkah submit/observasi), sehingga bug tidak bisa direproduksi orang lain. | Ditambahkan langkah aksi dan langkah observasi di akhir; typo 'beiside' dihapus.
BUG_002 - Summary | Summary sama persis dengan Description dan tidak menyebut field mana yang bermasalah. | Summary menyebut field yang terdampak (RNCP Title / Class / User) dan Description merujuk baris Test Case.
BUG_003 - Description & Actual Result | Typo: 'You cant delating the date after selected', 'Cannnot clear the data'. | Ejaan diperbaiki dan kalimat dirapikan.
BUG_005 s/d BUG_015 | Tidak ada. Test Case memuat 11 temuan lain (label FR salah, highlight menu, asterisk Priority, default Priority, 2 format tanggal, submit button, past date, search first name, pop up task Done, menu User) tanpa bug report. | Ditambahkan 11 bug report draft dengan format field yang sama. Attachment diisi '-' dan Reproducability Rate diisi 'to be confirmed' karena bukti/percobaan tidak tersedia di dokumen - harus dilengkapi tester.
Traceability | Tidak ada penghubung antara Bug Report dan Test Case, sehingga reviewer sulit mencocokkan temuan. | Ditambahkan sheet 'Bug List' berisi Bug ID, modul, severity, nomor baris Test Case, dan asal bug. Kolom Comment di Test Case juga sudah diberi 'Ref: BUG_xxx'.
Label field 'Reproducability Rate' | Ejaan yang benar adalah 'Reproducibility Rate'. | TIDAK diubah karena kemungkinan label bawaan template perusahaan. Silakan ubah jika template memang milik sendiri.
Konsistensi Environment | Sudah konsisten di 4 bug awal. | Blok Environment yang sama dipakai untuk semua bug baru.